## Sayfa1
PROJECT MANAGEMENT PLAN
|  |  | 1. Week | 2. Week | 3. Week | 4. Week | 5. Week | 6.Week | 7. Week | 8.Week | 9. Week | 10.Week | 11.Week | 12. Week | 13. Week | 14.Week | 15.Week | 16.Week
Job Definition | Task Group Areas of Responsibility | Situation | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15
Team Setup | Ahmet Selim YALÇIN | Completed | bar: 2023-10-02
Literature Study | Tüm Ekip | Continues | bar: 2023-10-09 to 2023-10-23
Mechanical Design Process | Burçak DOĞAN | Continues | bar: 2023-10-16 to 2023-10-23
Manufacturing Documentation | Burçak DOĞAN | Not started | bar: 2023-10-30 to 2023-11-13
Mechanical Production Process | Burçak DOĞAN | Not started | bar: 2023-11-13 to 2023-11-27
Mechanical Assembly | Burçak DOĞAN | Not started | bar: 2023-11-20 to 2023-12-04
Structural Analysis Tests | Burçak DOĞAN | Not started | bar: 2023-11-27 to 2023-12-11
Hardware Design Process | Mustafa Furkan EROĞLU | Continues | bar: 2023-10-30 to 2023-11-20
Electronic Card String | Mustafa Furkan EROĞLU | Not started | bar: 2023-11-13 to 2023-11-27
Cabling Production Process | Mustafa Furkan EROĞLU | Not started | bar: 2023-11-27 to 2023-12-04
Testing of Electronic Cards | Mustafa Furkan EROĞLU | Not started | bar: 2023-12-04 to 2023-12-18
Software Process | Barış Berker BAYRAM | Continues | bar: 2023-10-30 to 2023-12-18
Software Testing | Barış Berker BAYRAM | Not started | bar: 2023-12-18 to 2023-12-25
System Integration Process | Ahmet Selim YALÇIN | Not started | bar: 2023-11-06 to 2024-01-01
Stock control | Ahmet Selim YALÇIN | Not started | bar: 2023-10-23 to 2023-11-06
Supply Process | Ahmet Selim YALÇIN | Not started
System Testing | Ahmet Selim YALÇIN | Not started | bar: 2023-12-18 to 2024-01-08
Driving Test | Ahmet Selim YALÇIN | Not started | bar: 2024-01-01 to 2024-01-15
First Report Preparation | Tüm Ekip | Continues | bar: 2023-10-23 to 2024-01-08
First Report Presentation | Tüm Ekip | Not started | bar: 2024-01-15
Second Report Preparation | Tüm Ekip | Not started
Second Report Presentation | Tüm Ekip | Not started

## Sayfa2
PROJE YÖNETİM PLANI
17. Hafta | 18. Hafta | 19. Hafta | 20. Hafta | 21. Hafta | 22. Hafta | 23. Hafta | 24. Hafta | 25. Hafta | 26. Hafta | 27. Hafta | 28. Hafta | 29. Hafta | 30. Hafta | 31. Hafta | 32. Hafta | 33. Hafta | 34. Hafta | 35. Hafta | 36. Hafta | 37. Hafta | 38. Hafta
2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-08-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17